## Worksheet
Week | Date Range | Objective | Key Activities | Responsible Team/Person | Deadlines & Milestones | Progress Status | Risk Factors | Action Items
Week 1 | Mon, Apr 8 – Sun, Apr 14 | Set up operational workflows for Q2 | Review current processes; document SOPs; assign roles | Operations Manager | Complete SOP documentation by Apr 10 | In Progress | Lack of cross-team input | Schedule team alignment meeting
Week 2 | Mon, Apr 15 – Sun, Apr 21 | Implement new client onboarding system | Integrate CRM; train support staff; launch pilot with 3 clients | IT & Customer Support Team | Pilot launch by Apr 19; full rollout by Apr 25 | Not Started | System integration delays | Finalize integration plan by Apr 12
Week 3 | Mon, Apr 22 – Sun, Apr 28 | Conduct quarterly performance review | Analyze KPIs; identify bottlenecks; present findings to leadership | Operations & Finance Teams | Review report submitted by Apr 27 | Planned | Data availability issues | Verify data sources by Apr 20
Week 4 | Mon, Apr 29 – Sun, May 5 | Optimize supply chain delivery times | Review delivery logs; renegotiate vendor SLAs; track improvements | Logistics & Procurement Team | Improve on-time delivery rate by 15% by May 3 | Not Started | Vendor capacity constraints | Engage vendors for capacity assessment by Apr 30
Week 5 | Mon, May 6 – Sun, May 12 | Review and update KPIs for Q2 | Collect performance data; adjust targets; align with strategy goals | Strategy & Analytics Team | KPI review presentation by May 10 | Not Started | Incomplete data from sales team | Request missing data from sales by May 3