## Annual Budget - Analysis View
ANNUAL BUDGET REPORT - ANALYSIS VIEW
Client Name | Project Name | Department | Budget Period | Initial Budget (USD) | Actual Spend (USD) | Variance (USD) | Variance % | Budget Utilization % | Forecasted Spend (USD) | Remaining Budget (USD) | Status
Q1 2024 - Project Launch Phase
Acme Corporation | Website Redesign | Marketing | Jan 01 - Mar 31, 2024 | $50,000.00 | $42,358.75 | $7,641.25 | 15.3% | 84.7% | $48,000.00 | $2,358.75 | On Track
Global Tech Inc. | Cloud Infrastructure Upgrade | IT Services | Jan 01 - Mar 31, 2024 | $75,000.00 | $74,892.50 | $107.50 | +1.4% | 99.86% | $76,500.00 | $-1,492.50 | At Risk
Urban Retail Group | Customer Loyalty Program | Sales & Marketing | Jan 01 - Mar 31, 2024 | $65,000.00 | $38,745.98 | $26,254.02 | 41.3% | 59.6% | $61,000.00 | $3,745.98 | Delayed
Q2 2024 - Execution & Optimization Phase
Acme Corporation | Website Redesign | Marketing | Apr 01 - Jun 30, 2024 | $65,000.00 | $47,895.32 | $17,104.68 | 26.3% | 73.7% | $55,000.00 | $19,895.32 | On Track
Global Tech Inc. | Cloud Infrastructure Upgrade | IT Services | Apr 01 - Jun 30, 2024 | $85,000.00 | $79,234.66 | $5,765.34 | 8.1% | 93.2% | $87,000.00 | $2,234.66 | On Track
Urban Retail Group | Customer Loyalty Program | Sales & Marketing | Apr 01 - Jun 30, 2024 | $55,000.00 | $49,678.15 | $5,321.85 | 17.3% | 90.3% | $54,000.00 | $9,678.15 | On Track
Annual Totals (Jan - Dec 2024)
Total Budgeted |  |  |  | $395,000.00 | $372,817.46 | $22,182.54 | 6.4% | 94.4% | $370,500.00 | $37,182.54 | Overall: On Track
Note: All figures in USD. Forecasted spend is based on current trend analysis.