## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T001 | Requirement Gathering | 2023-10-01 | 2023-10-15 | Completed | 100%
T002 | Design Phase | 2023-10-16 | 2023-11-05 | In Progress | 65%
T003 | Development Sprint 1 | 2023-11-06 | 2023-11-24 | In Progress | 45%
T004 | Testing & QA | 2023-11-25 | 2023-12-15 | Delayed | 30%
T005 | Client Review & Feedback | 2023-12-16 | 2024-01-15 | In Progress | 20%
T006 | Deployment | 2024-01-16 | 2024-01-31 | Delayed | 5%
Legend
Completed
In Progress
Delayed