## Worksheet
Client Reporting - Gantt Chart (Basic)
Task ID | Task Name | Start Date | End Date | Status | % Complete
T1 | Project Initiation | 2024-04-01 | 2024-04-15 | In Progress | 75%
T2 | Data Collection | 2024-04-16 | 2024-05-10 | In Progress | 50%
T3 | Data Analysis | 2024-05-11 | 2024-06-15 | Not Started | 0%
T4 | Report Drafting | 2024-06-16 | 2024-07-31 | Not Started | 0%
T5 | Client Review & Feedback | 2024-08-01 | 2024-08-15 | Not Started | 0%
T6 | Final Report Delivery | 2024-08-16 | 2024-08-31 | Not Started | 0%