## Worksheet
Project Gantt Chart - Client Reporting
Business Use Template ¦ Version 1.0
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
1 | Project Initiation & Planning | 2024-01-05 | 2024-01-19 | In Progress
1.1 | Client Requirements Gathering | 2024-01-05 | 2024-01-12 | In Progress
1.2 | Project Scope Definition | 2024-01-13 | 2024-01-19 | In Progress
2 | Design & Development Phase | 2024-01-20 | 2024-03-15 | Not Started
2.1 | User Interface Design | 2024-01-20 | 2024-01-31 | Not Started
2.2 | Backend Development | 2024-01-31 | 2024-03-15 | Not Started
3 | Testing & Quality Assurance | 2024-03-16 | 2024-03-31 | Not Started
3.1 | System Integration Testing | 2024-03-16 | 2024-03-25 | Not Started
3.2 | User Acceptance Testing (UAT) | 2024-03-26 | 2024-03-31 | Not Started
M1 | Project Kickoff | 2024-01-05 | 2024-01-05 | Completed
M2 | Client Sign-Off on Design | 2024-01-31 | 2024-01-31 | Not Started
M3 | Project Final Delivery | 2024-04-01 | 2024-04-01 | Not Started