## Worksheet
Client Reporting - Gantt Chart Dashboard View
Project Timeline Overview ¦ Updated: October 5, 2023
Task ID | Task Name | Start Date | End Date | Status | Progress (%) | Timeline (Weeks)
001 | Project Initiation | 2023-10-02 | 2023-10-15 | High Priority | 95%
002 | Requirement Gathering | 2023-10-16 | 2023-11-05 | In Progress | 75%
003 | Design Phase | 2023-11-06 | 2023-11-26 | In Progress | 45%
004 | Development | 2023-11-27 | 2024-01-15 | Pending | 5%
005 | Testing & QA | 2024-01-16 | 2024-01-31 | Pending | 0%
006 | Deployment | 2024-02-01 | 2024-02-15 | Pending | 0%
007 | Post-Implementation Review | 2024-02-16 | 2024-03-15 | Pending | 0%
Total Project Duration: | [5 empty] | From 2023-10-02 to 2024-03-15
Generated on October 5, 2023 ¦ Dashboard View - Client Reporting