## Worksheet
Task ID | Task Name | Start Date | End Date | % Complete | Status
T001 | Project Initiation | 2024-04-01 | 2024-04-15 | 100% | In Progress
T002 | Requirement Gathering | 2024-04-16 | 2024-05-15 | 85% | In Progress
T003 | Design Phase | 2024-05-16 | 2024-06-30 | 65% | In Progress
T004 | Development Phase | 2024-07-01 | 2024-08-31 | 35% | In Progress
T005 | Testing & QA | 2024-09-01 | 2024-10-31 | 15% | In Progress
M01 | Project Launch (Milestone) | 2024-11-01 | 2024-11-03 | 0% | Milestone
Note:This table represents a data version of a Gantt chart for client reporting. For visual timeline representation, consider exporting to Excel and using conditional formatting or built-in Gantt chart tools.