## Worksheet
Client Reporting Gantt Chart (Detailed)
Task ID | Task Name | Start Date | Due Date | Status | % Complete | Resource(s)
P1 | Project Initiation & Requirements Gathering | 2025-04-05 | 2025-04-18 | In Progress | 75% | Jane Doe, Alex Lee
P2 | UI/UX Design & Wireframing | 2025-04-19 | 2025-05-16 | In Progress | 40% | Samir Patel
M1 | Design Approval – Client Sign-Off | 2025-05-17 | 2025-05-17 | Pending | — | Client, Jane Doe
P3 | Frontend Development | 2025-05-18 | 2025-06-19 | Not Started | 0% | Chris Brown, Taylor Kim
P4 | Backend Development | 2025-05-18 | 2025-06-19 | Not Started | 0% | James Wilson
P5 | System Integration & QA Testing | 2025-06-20 | 2025-07-17 | Not Started | 0% | Emma Garcia, Leo Chen
M2 | Testing Complete & UAT Sign-Off | 2025-07-18 | 2025-07-18 | Pending | — | Client, QA Team
P6 | Deployment to Production | 2025-07-19 | 2025-07-19 | Pending | — | DevOps Team, James Wilson
P7 | Post-Deployment Support & Client Training | 2025-07-20 | 2025-08-15 | Pending | 0% | Jane Doe, Samir Patel
Last Updated: April 5, 2025 ¦ Generated via Client Reporting Gantt Chart Template (Detailed)