## Worksheet
Client Reporting - Extended Gantt Chart
Project: Strategic Market Expansion ¦ Period: Q3 2024 ¦ Last Updated: June 5, 2024
Task / Milestone | Start Date | End Date | Duration (Days) | Progress | Timeline View | Status
Phase 1: Market Research & Analysis
Market Segmentation Study | Jul 01, 2024 | Jul 15, 2024 | 15 days |  | [=====¦-------] | In Progress
Competitor Benchmarking | Jul 05, 2024 | Jul 20, 2024 | 16 days |  | [===¦--------] | In Progress
Phase 1 Final Report Submission | Jul 25, 2024 | Jul 25, 2024 | 1 day | ⭕ | [●] | Completed
Phase 2: Strategy Development & Approval
Strategic Plan Draft | Jul 26, 2024 | Aug 10, 2024 | 16 days |  | [==¦--------] | In Progress
Internal Review Session | Aug 08, 2024 | Aug 10, 2024 | 3 days | - | [-----¦---] | Delayed
Strategic Plan Final Approval | Aug 15, 2024 | Aug 15, 2024 | 1 day | ⭕ | [●] | Completed
Phase 3: Pilot Launch & Monitoring
Pilot Site Selection | Aug 16, 2024 | Aug 31, 2024 | 16 days | - | [--¦--------] | Completed
Pilot Program Execution | Sep 01, 2024 | Oct 15, 2024 | 45 days | [----¦-------] | [---¦--------] | In Progress
End of Pilot Evaluation | Oct 15, 2024 | Oct 15, 2024 | 1 day | ⭕ | [●] | Delayed
Phase 4: Full Rollout & Reporting
Full Market Launch | Oct 16, 2024 | Dec 31, 2024 | 76 days | [----¦------] | [----¦--------] | Delayed
Final Client Report Submission | Dec 31, 2024 | Dec 31, 2024 | 1 day | ⭕ | [●] | Delayed