## Worksheet
Client Reporting - Freelancer Gantt Chart
Task Name | Start Date | Due Date | Status | Progress
Phase 1: Project Setup
Initial Client Meeting | 2024-04-15 | 2024-04-18 | Completed
Requirement Analysis | 2024-04-19 | 2024-04-25 | Completed
Phase 2: Design Phase
Wireframe Development | 2024-04-26 | 2024-05-03 | Completed
UI/UX Design Finalization | 2024-05-04 | 2024-05-10 | Completed
Phase 3: Development
Frontend Implementation | 2024-05-13 | 2024-06-15 | In Progress
Backend Integration | 2024-05-13 | 2024-06-17 | In Progress
Phase 4: Testing
Functional Testing | 2024-06-18 | 2024-06-25 | Delayed
Phase 5: Final Delivery
Client Review & Feedback | 2024-06-26 | 2024-07-03 | Not Started
This report was generated on¦ Freelancer Gantt Chart Template