## Worksheet
Client Reporting - Large Business Gantt Chart
Task / Milestone | Start Date | End Date | Duration (Days) | Progress
Phase 1 - Discovery
Project Kickoff Meeting | 2024-04-15 | 2024-04-15 | 1
Client Requirements Gathering | 2024-04-16 | 2024-04-30 | 15
Phase 2 - Design
Wireframe Development | 2024-05-01 | 2024-05-15 | 15
UI/UX Design Approval | 2024-05-16 | 2024-05-31 | 16
Phase 3 - Development
Front-End Implementation | 2024-06-01 | 2024-07-15 | 45
Back-End Integration | 2024-06-15 | 2024-08-31 | 78
Phase 4 - Testing
System Integration Testing | 2024-08-15 | 2024-09-15 | 31
User Acceptance Testing (UAT) | 2024-09-16 | 2024-10-31 | 45
Phase 5 - Launch
Final Production Deployment | 2024-11-01 | 2024-11-03 | 3
Generated on¦ This Gantt chart is for internal client reporting purposes.