## Worksheet
Client Reporting - Gantt Chart (Manager View)
Project Timeline and Task Progress Overview
Task Name | Start Date | Due Date | Duration (Days) | Progress | Status
Project Initiation | 2023-10-01 | 2023-10-05 | 5 |  | Completed
Requirement Gathering | 2023-10-06 | 2023-10-15 | 10 |  | In Progress
Design Phase | 2023-10-16 | 2023-10-30 | 15 |  | In Progress
Development Sprint 1 | 2023-10-31 | 2023-11-15 | 16 |  | In Progress
Testing & QA | 2023-11-16 | 2023-11-30 | 15 |  | In Progress
User Training | 2023-12-01 | 2023-12-07 | 7 |  | In Progress
Deployment & Go-Live | 2023-12-08 | 2023-12-15 | 8 |  | Not Started
Post-Implementation Review | 2023-12-16 | 2023-12-31 | 16 |  | Not Started