## Worksheet
Client Reporting - Project Timeline
Project Name: Strategic Digital Transformation ¦ Report Period: Q3 2024 ¦ Generated On: October 5, 2024
Task ID | Task Description | Start Date | End Date | Duration (Days) | Progress
PRJ-001 | Project Initiation & Planning | 2024-07-01 | 2024-07-15 | 15
PRJ-002 | Requirements Gathering | 2024-07-16 | 2024-07-31 | 16
PRJ-003 | Design Phase - UI/UX | 2024-08-01 | 2024-08-15 | 15
PRJ-004 | Development - Frontend | 2024-08-16 | 2024-09-30 | 46
PRJ-005 | Development - Backend | 2024-08-16 | 2024-10-15 | 61
PRJ-006 | Integration Testing | 2024-10-16 | 2024-11-30 | 46
PRJ-007 | User Acceptance Testing (UAT) | 2024-12-01 | 2024-12-15 | 15
MS-001 | Project Kickoff | 2024-07-01 | 2024-07-01 | 1
MS-002 | Design Finalization | 2024-08-15 | 2024-08-15 | 1
MS-003 | Development Complete | 2024-10-15 | 2024-10-15 | 1
MS-004 | Project Launch | 2024-12-16 | 2024-12-16 | 1
Page 1 of 3 ¦ Generated by Client Reporting System v2.0 ¦ Confidential – For Internal Use Only
Client Reporting - Project Timeline (Cont.)
Project Name: Strategic Digital Transformation ¦ Report Period: Q3 2024 ¦ Generated On: October 5, 2024
Task ID | Task Description | Start Date | End Date | Duration (Days) | Progress
PRJ-008 | Training & Documentation | 2024-12-17 | 2024-12-31 | 15
PRJ-009 | Post-Launch Review | 2024-12-16 | 2025-01-15 | 31
PRJ-010 | Performance Monitoring | 2025-01-16 | 2025-03-31 | 76
PRJ-011 | Quarterly Review & Optimization | 2025-04-01 | 2025-06-30 | 91
MS-005 | UAT Completion | 2024-12-15 | 2024-12-15 | 1
MS-006 | Final Documentation Handover | 2025-01-15 | 2025-01-15 | 1
Page 2 of 3 ¦ Generated by Client Reporting System v2.0 ¦ Confidential – For Internal Use Only
Client Reporting - Project Timeline (Final)
Project Name: Strategic Digital Transformation ¦ Report Period: Q3 2024 ¦ Generated On: October 5, 2024
Task ID | Task Description | Start Date | End Date | Duration (Days) | Progress
PRJ-012 | Client Feedback Analysis | 2025-07-01 | 2025-07-31 | 31
PRJ-013 | Phase II Planning | 2025-08-01 | 2025-10-31 | 92
MS-007 | Project Closure | 2025-11-30 | 2025-11-30 | 1
PRJ-014 | Final Audit & Reporting | 2025-12-01 | 2026-01-31 | 62