## Worksheet
Client Reporting - Gantt Chart Template (Personal Use)
Task | Start Date | End Date | Duration (Days) | Progress
Project Phase 1: Planning & Discovery
Requirement Gathering | 2024-04-01 | 2024-04-15 | 15
Client Workshops | 2024-04-16 | 2024-04-25 | 10
Project Phase 2: Development
UI/UX Design | 2024-04-26 | 2024-05-15 | 20
Backend Implementation | 2024-05-16 | 2024-06-15 | 31
Project Phase 3: Testing & Delivery
Integration Testing | 2024-06-16 | 2024-06-30 | 15
User Acceptance Testing (UAT) | 2024-07-01 | 2024-07-15 | 15
Project Phase 4: Post-Launch
Deployment & Go-Live | 2024-07-16 | 2024-07-16 | 1
Maintenance & Support | 2024-07-17 | Ongoing | Open-ended
Template for Personal Use – Client Reporting Gantt Chart