## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | 2025-04-01 | 2025-04-15 | In Progress
T002 | Requirements Gathering | 2025-04-16 | 2025-05-14 | In Progress
T003 | Design Phase | 2025-05-15 | 2025-06-19 | Pending
T004 | Development Phase | 2025-06-20 | 2025-11-30 | Pending
T005 | Testing & QA | 2025-12-01 | 2026-01-31 | Pending
MS01 | Project Launch | 2026-02-15 | 2026-02-15 | Milestone - Final Delivery & Handover
Total Duration: |  |  |  | 210 Days