## Client Reporting - Gantt Chart
Client Reporting - Gantt Chart
Project Timeline and Progress Report ¦ Printed on:
Task | Start Date | End Date | Progress | Timeline (Monthly)
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul
Data Collection & Analysis | 2024-01-05 | 2024-03-15 | 75%
Report Drafting | 2024-03-18 | 2024-05-10 | 65%
Review & Feedback | 2024-05-13 | 2024-06-15 | 35%
Final Report Submission | 2024-06-18 | 2024-06-30 | 15%
Client Presentation | 2024-07-03 | 2024-07-15 | 5%