## Client Reporting - Gantt Chart
Client Reporting - Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
T001 | Project Initiation | 2023-10-01 | 2023-10-05 | 5 | Completed
T002 | Requirements Gathering | 2023-10-06 | 2023-10-15 | 10 | Completed
T003 | Design Phase | 2023-10-16 | 2023-11-05 | 21 | In Progress
T004 | Development Sprint 1 | 2023-11-06 | 2023-11-25 | 20 | In Progress
T005 | Testing & QA | 2023-11-26 | 2023-12-15 | 20 | Delayed
T006 | Client Review & Feedback | 2023-12-16 | 2023-12-31 | 16 | Delayed
T007 | Final Deployment | 2024-01-01 | 2024-01-15 | 15 | Delayed
Report generated on¦ Last updated: