## Worksheet
Client Reporting - Gantt Chart - Report Version
Task ID | Task Name | Start Date | End Date | Status | Progress
T001 | Project Initiation | 2023-10-05 | 2023-10-15 | Complete
Requirement Gathering | Client Requirements Finalization | 2023-10-16 | 2023-10-31 | Complete
T003 | Design Phase | 2023-11-01 | 2023-11-15 | Complete
T004 | Development Phase | 2023-11-16 | 2023-12-31 | Ongoing
T005 | Testing & QA | 2024-01-01 | 2024-01-31 | Delayed
T006 | Client Review & Feedback | 2024-02-01 | 2024-02-15 | Complete
T007 | Final Deployment | 2024-02-16 | 2024-03-15 | Ongoing
T008 | Post-Implementation Review | 2024-03-16 | 2024-04-15 | Complete
Project Summary: |  |  |  | Overall Complete
Legend:
Complete– Task finished successfully.
Ongoing– In progress but not finished.
Delayed– Behind schedule.