## Client Reporting - Gantt Chart
Client Reporting - Gantt Chart (Simple Style)
Task | Start Date | End Date | Status | % Complete
Project Initiation | 2024-01-01 | 2024-01-15 | In Progress | 75%
Requirements Gathering | 2024-01-16 | 2024-01-31 | In Progress | 60%
Design Phase | 2024-02-01 | 2024-02-15 | Not Started | 0%
Development Phase | 2024-02-16 | 2024-03-31 | Not Started | 0%
Testing & QA | 2024-04-01 | 2024-04-30 | Not Started | 0%
Milestone: Project Kickoff | 2024-01-01 | 2024-01-01 | Completed | 100%
Milestone: Requirements Approved | 2024-01-31 | 2024-01-31 | Not Started | 0%
Legend:
Milestone– Key milestone events
Task– Regular project tasks