## Worksheet
Client Reporting Gantt Chart - Small Business
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T101 | Project Planning | 2025-04-01 | 2025-04-07 | In Progress | 85%
T102 | Client Onboarding | 2025-04-08 | 2025-04-14 | In Progress | 65%
T103 | Data Collection | 2025-04-15 | 2025-04-21 | Pending | 0%
T104 | Analysis Phase | 2025-04-22 | 2025-04-30 | Not Started | 0%
T105 | Report Drafting | 2025-05-01 | 2025-05-14 | Not Started | 0%
T106 | Client Review | 2025-05-15 | 2025-05-21 | Not Started | 0%
T107 | Final Report Submission | 2025-05-22 | 2025-05-31 | Not Started | 0%
This Gantt chart is intended for client reporting in a small business context. All dates are subject to change.