## Worksheet
Client Reporting Gantt Chart
Startup Version - Project Timeline & Status Overview
Task / Milestone | Owner | Start Date | End Date | Status | Gantt Chart View
Market Research & Validation | Marketing Team | 2024-06-01 | 2024-06-15 | Completed | Jun 1 – Jun 15, 2024
Product Design Phase | Design Team | 2024-06-16 | 2024-07-15 | In Progress
Prototype Development | Engineering Team | 2024-07-16 | 2024-08-15 | In Progress
Beta Testing (Internal) | QA Team | 2024-08-16 | 2024-09-15 | Delayed
User Feedback Integration | Product Team | 2024-09-16 | 2024-10-31 | In Progress
Launch Preparation & Marketing | Marketing Team | 2024-11-01 | 2024-11-30 | In Progress
Official Product Launch | CEO & Exec Team | 2024-12-01 | 2024-12-31 | Delayed
Generated on¦ Version: Startup - Gantt Chart v1.0