## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress | Status
Project Initiation | 2023-10-01 | 2023-10-05 | 5 |  | Completed
Requirements Gathering | 2023-10-06 | 2023-10-15 | 10 |  | In Progress
Design Phase | 2023-10-16 | 2023-10-30 | 15 |  | In Progress
Development | 2023-10-31 | 2023-12-15 | 45 |  | Not Started
Testing & QA | 2023-12-16 | 2024-01-15 | 31 |  | Not Started
Deployment | 2024-01-16 | 2024-01-31 | 16 |  | Not Started
Post-Implementation Review | 2024-02-01 | 2024-02-15 | 15 |  | Not Started
Total Duration | 150 Days (Approx.)