## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assignee | Status
T001 | Project Kickoff Meeting | 2023-10-02 | 2023-10-03 | 2 | Alice Johnson | Complete
T002 | Requirements Gathering | 2023-10-04 | 2023-10-15 | 12 | Bob Smith | 75%
T003 | Design Phase | 2023-10-16 | 2023-10-27 | 12 | Catherine Lee | 50%
T004 | Development Sprint 1 | 2023-10-28 | 2023-11-15 | 18 | Daniel Brown | 30%
T005 | Development Sprint 2 | 2023-11-16 | 2023-12-08 | 23 | Daniel Brown | 5%
T006 | Testing & QA | 2023-12-09 | 2023-12-31 | 23 | Ella Martinez | 0%
T007 | User Training Session | 2024-01-01 | 2024-01-15 | 15 | Finn Wilson | 0%
T008 | Project Delivery & Closure | 2024-01-16 | 2024-01-31 | 16 | Alice Johnson | Not Started
Legend:
• Milestone Tasks are highlighted in yellow.