## Worksheet
Client Reporting - Home Template - Detailed
CLIENT OVERVIEW & PERFORMANCE METRICS
Client Details |  | Reporting Period: January 1, 2024 - March 31, 2024
Client Name: | GlobalTech Solutions Inc. | Primary Contact: | Jane Smith (Director of Operations) | Email: | jane.smith@globaltech.com
KPIs & Performance Indicators |  | Target vs. Actual Results
Revenue Growth (YoY): | 18.5% | Target: | 15.0% | Performance Status | Above Target
Customer Satisfaction (CSAT): | 93.2% | Target: | 90.0%
PROJECT STATUS & PROGRESS TRACKING
Project Name | Status | Progress (%) | Start Date | Target End Date | Actual Completion Date
Data Migration & Integration | In Progress | 78% | Jan 5, 2024 | Mar 30, 2024 | Apr 15, 2024
CRM System Upgrade | On Track | 91% | Jan 15, 2024 | Mar 31, 2024 | Mar 30, 2024
Marketing Automation Setup | Delayed | 56% | Feb 1, 2024 | Pending - Resource Constraints
FINANCIAL SUMMARY & BUDGET UTILIZATION
Budget Allocated: | $285,000 | Expenses to Date: | $237,850 | Utilization: 83.4%
RISK & ISSUE LOG
Issue Description | Severity | Impact Level | Status | Owner | Resolution Target Date
Data privacy compliance gap identified in new CRM system. | High | Medium | In Progress | IT Security Team | May 10, 2024
Delayed vendor delivery of integration API. | High | High | Open | Project Manager | May 1, 2024
NEXT STEPS & ACTION ITEMS
Key Actions: 1. Finalize CRM security review by April 20 2. Secure additional development resources for Marketing Automation by April 10 3. Schedule client feedback session on March 18 |  |  | Action Owner: John Doe (Project Lead) Due: April 25, 2024
This report was generated on April 5, 2024. For questions or updates, contact the Client Success Team.