## Worksheet
Monthly Planner - Client Reporting
Company:ABC Consulting Group
Contact:john.doe@abcconsult.com ¦ (555) 123-4567
Client:Global Solutions Inc.
Reporting Period:January 2024
Status:Draft
Date | Task/Activity | Owner | Status | Target Completion | Actual Completion
Jan 02, 2024 | Initial client onboarding meeting | Jane Smith | In Progress | Jan 05, 2024
Jan 05, 2024 | Review client requirements document | Mike Johnson | Completed | Jan 07, 2024 | Jan 06, 2024
Jan 10, 2024 | Develop project timeline and milestones | Sarah Lee | In Progress | Jan 15, 2024
Jan 12, 2024 | Client feedback session - Phase I deliverables | Jane Smith | Pending Review | Jan 14, 2024
Jan 18, 2024 | Update project plan based on feedback | Mike Johnson | Pending Review | Jan 20, 2024
Jan 25, 2024 | Finalize Phase I deliverables for client approval | Sarah Lee | Pending Review | Jan 30, 2024
Total Tasks: 7 ¦ Completed: 1 ¦ In Progress: 3 ¦ Pending: 3
This report was generated on January 3, 2024 at 14:35. All data is subject to change until final approval. For questions or corrections, please contact the project management team.