## Worksheet
Monthly Client Reporting Planner
Client Name: _________________________ ¦ Month: _______________ ¦ Year: ________
Date | Activity/Task | Progress & Status |  |  | Notes/Comments
|  | Target Completion Date | Actual Completion Date | Status (✓/✗)
01/04/2025 | Project Kickoff Meeting | 05/04/2025
05/04/2025 | Requirement Gathering Phase | 15/04/2025
15/04/2025 | Design Review Session | 20/04/2025
20/04/2025 | Development Sprint 1 | 30/04/2025
30/04/2025 | Initial Testing & QA | 05/05/2025
07/05/2025 | Client Feedback Session | 10/05/2025
10/05/2025 | Final Adjustments & Fixes | 15/05/2025
15/05/2025 | Final Review & Sign-off | 17/05/2025
17/05/2025 | Deployment to Production | 18/05/2025
18/05/2025 | Post-Deployment Review | 20/05/2025
20/05/2025 | Monthly Reporting Submission | 31/05/2025
31/05/2025 | Monthly Retrospective Meeting | 31/05/2025
Page 1 of 4 ¦ Report generated on: _______________ ¦ Prepared by: __________________
Monthly Client Reporting Planner
Client Name: _________________________ ¦ Month: _______________ ¦ Year: ________
Key Performance Indicator (KPI) | Target Value | Actual Value | Variance (%)
Project Delivery On-Time Rate | 95%
Client Satisfaction Score (CSAT) | 4.8/5.0
Bug Resolution Rate | 98%
Client Engagement Level | High (≥3 meetings/month)
Budget Adherence | ±5%
Monthly Summary & Key Highlights:
Page 2 of 4 ¦ Report generated on: _______________ ¦ Prepared by: __________________
Monthly Client Reporting Planner
Client Name: _________________________ ¦ Month: _______________ ¦ Year: ________
Budget Category | Allocated Budget ($) | Spent ($) | Remaining ($)
Project Management | 5,000
Development & Design | 15,000
Testing & QA | 3,500
Client Meetings & Training | 2,000
Contingency (10%) | 2,550
Total Budget | 28,050
Risk & Issue Log:
Issue/Risk | Impact Level | Probability | Status (Open/Closed) | Action Taken/Planned
Delayed client feedback on deliverables | Medium | High | Open | Schedule follow-up call every Friday.
Resource availability constraints in week 3 | High | Medium | Open | Raised with team leads for rescheduling.
Bug discovery in final QA phase | High | Low | Closed | Patched and verified by QA team.
Page 3 of 4 ¦ Report generated on: _______________ ¦ Prepared by: __________________
Monthly Client Reporting Planner
Client Name: _________________________ ¦ Month: _______________ ¦ Year: ________
Client Feedback Summary:
Next Month Planning (Preview):
Activity/Task | Scheduled Start Date | Potential Challenges
System Upgrade Implementation | 05/06/2025 | Integration testing complexity
New Feature Development Sprint 1 | 10/06/2025 | Requirement changes from client
Quarterly Business Review Meeting | 25/06/2025 | Scheduling conflict with other clients
Prepared by: Signature _________________________ Name: ___________________________ Date: _______________ |  | Reviewed by (Client): Signature _________________________ Name: ___________________________ Date: _______________