## Worksheet
CLIENT REPORTING - MANAGER VIEW PLANNER TEMPLATE
Client Name | Project ID | Reporting Period | Status | Scheduled Review Date | Next Milestone | Owner (Manager) | Budget Allocated ($) | Budget Used ($) | % Complete | Risk Level | Action Items
Acme Corp | PROJ-2024-001 | Jan 2024 - Mar 2024 | On Track | Mar 15, 2024 | Final Deliverables Review | Jane Smith | $75,000 | $63,200 | 84% | Medium Risk | Update client dashboard, confirm QA sign-off
Innovatech Inc. | PROJ-2024-005 | Jan 2024 - Mar 2024 | On Track | Mar 18, 2024 | Final Testing Phase | Robert Lee | $95,000 | $78,500 | 83% | Low Risk | Schedule UAT session with stakeholders
Global Solutions Ltd. | PROJ-2024-010 | Jan 2024 - Mar 2024 | Delayed | Mar 30, 2024 | Revised Timeline Approval | Lisa Chen | $58,000 | $41,300 | 71% | High Risk | Finalize revised timeline with client; address resource constraints.
TechNova Systems | PROJ-2024-015 | Jan 2024 - Mar 2024 | On Track | Mar 10, 2024 | Deployment & Go-Live | Mark Johnson | $120,000 | $95,750 | 80% | Medium Risk (Pending Approval) | Final approval from CTO required before deployment.
NextGen Digital | PROJ-2024-020 | Jan 2024 - Mar 2024 | On Track | Mar 13, 2024 | User Training Sessions | Sophia Brown | $65,000 | $47,800 | 73% | Low Risk | Coordinate training schedules with client HR team.
This document is generated as a Manager View Planner Template for Client Reporting. Data updates are recommended weekly.