## Worksheet
Project Plan - Advanced Template
PROJECT OVERVIEW
Project ID | Project Name | Client Name | Manager | Status | Budget (USD) | Timeline Overview
PJ-2024-018 | NextGen CRM Implementation | InnovateCorp Inc. | Sarah Johnson | On Track | $275,000.00 | Start: Jan 15, 2024 Target End: Jun 30, 2024 Duration: 5 months
TASK SCHEDULE & PROGRESS
Task ID | Task Description | Assigned To | Schedule (Start - End) |  | Progress (%) |  | Status
TSK-01 | Requirements Gathering & Analysis | Mark Reed, Analyst | Jan 15 - Feb 10, 2024 |  | 95% |  | Complete
TSK-02 | UI/UX Design Phase 1 | Lena Patel, Designer | Feb 13 - Mar 05, 2024 |  | 100% |  | Complete
TSK-03 | Backend Development (Core Module) | Juan Morales, Developer | Mar 08 - Apr 25, 2024 |  | 78% |  | On Track
TSK-04 | Frontend Integration & Testing | Aisha Khan, Developer | Apr 26 - May 15, 2024 |  | 35% |  | At Risk
TSK-05 | User Acceptance Testing (UAT) | Daniel Brown, QA Lead | May 16 - May 31, 2024 |  | 0% |  | Not Started
TSK-06 | Deployment & Go-Live | Ryan Clark, DevOps | Jun 01 - Jun 30, 2024 |  | 0% |  | Not Started
Total Tasks: | [6 empty] | 6
Key Metrics |  |  |  | On Track: 3 ¦ At Risk: 1 ¦ Not Started: 2 Avg. Progress Rate: 60.5%