## Worksheet
Project Phase | Key Deliverables | Start Date | End Date | Status | Responsible Team
Initiation & Planning | Project Charter, Scope Statement, Risk Assessment | 2024-01-05 | 2024-01-31 | In Progress | Project Management Office
Requirement Analysis | User Requirements Document, Stakeholder Sign-off | 2024-02-01 | 2024-03-15 | To Do | Business Analysts
Design Phase | System Architecture, UI/UX Mockups, Technical Specifications | 2024-03-16 | 2024-05-15 | To Do | Design & Dev Team
Development & Testing | Code Implementation, Unit Testing, Integration Testing | 2024-05-16 | 2024-08-31 | To Do | Development Team
User Acceptance Testing (UAT) | Test Cases, Feedback Report, Sign-off from Client | 2024-09-01 | 2024-10-15 | To Do | Client & QA Team
Deployment & Go-Live | Production Deployment, Training Materials, Go-Live Support | 2024-10-16 | 2024-11-30 | To Do | DevOps & Support Team
Post-Launch Review & Optimization | Performance Report, Client Feedback, Improvement Plan | 2024-12-01 | 2024-12-31 | To Do | Project Managers & Analysts