## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Progress (%)
1 | Project Initiation | 2023-10-01 | 2023-10-05 | John Doe | Completed | 100%
2 | Requirements Gathering | 2023-10-06 | 2023-10-15 | Jane Smith | In Progress | 60%
3 | Design Phase | 2023-10-16 | 2023-10-30 | Alex Johnson | Not Started | 0%
4 | Development | 2023-10-31 | 2023-12-15 | Team A | Not Started | 0%
5 | Testing | 2023-12-16 | 2024-01-10 | QA Team | Not Started | 0%
6 | Deployment | 2024-01-11 | 2024-01-15 | DevOps Team | Not Started | 0%
7 | Project Closure | 2024-01-16 | 2024-01-20 | Project Manager | Not Started | 0%