## Project Plan - Client View
Project Plan - Client View
Phase / Task | Start Date | End Date | Status | Owner | Budget (USD)
Project Initiation & Planning | 2024-01-05 | 2024-01-15 | In Progress | Jane Smith (PM) | $7,500
Requirements Gathering & Analysis | 2024-01-16 | 2024-01-31 | Pending | Mike Johnson (BA) | $5,800
Design & Prototyping | 2024-02-01 | 2024-02-15 | Pending | Sarah Lee (UX) | $9,300
Development Phase 1 - Core Features | 2024-02-16 | 2024-03-15 | Pending | Tom Brown (Dev Lead) | $38,500
Development Phase 2 - Reporting Module | 2024-03-16 | 2024-04-15 | Pending | Tom Brown (Dev Lead) | $31,700
Testing & QA Validation | 2024-04-16 | 2024-05-15 | Pending | Lisa Wong (QA Manager) | $18,900
User Acceptance Testing (UAT) | 2024-05-16 | 2024-06-15 | Pending | Client Team (UAT) | $6,800
Deployment & Go-Live | 2024-06-16 | 2024-07-15 | Pending | John Davis (Ops) | $9,500
Post-Launch Support & Review | 2024-07-16 | 2024-10-15 | Pending | All Team Members | $35,800
Total Project Budget: |  |  |  |  | $163,800
Note:This project plan is a high-level overview. Actual timelines and deliverables may be adjusted based on client feedback and evolving requirements.