## Project Plan - Compact Template
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
Phase 1: Project Initiation
P001 | Define Project Scope | John Doe | 2023-10-02 | 2023-10-15 | In Progress | 75%
Phase 2: Design & Planning
P002 | Create System Architecture | Jane Smith | 2023-10-16 | 2023-11-05 | Not Started | 0%
Phase 3: Development
P003 | Frontend Development | Mike Johnson | 2023-11-06 | 2024-01-15 | Not Started | 0%
Phase 4: Testing & QA
P004 | Unit Testing | Alice Brown | 2024-01-16 | 2024-02-15 | Not Started | 0%
Phase 5: Deployment & Closeout
P005 | Deployment to Production | Robert Wilson | 2024-02-16 | 2024-03-15 | Not Started | 0%
Overall Progress: | [5 empty] | 25%