## Project Plan Dashboard View
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%)
PJ001 | Project Initiation | Alice Johnson | 2024-04-01 | 2024-04-15 | Completed
PJ002 | Requirements Gathering | Bob Smith | 2024-04-16 | 2024-05-15 | In Progress
PJ003 | Design Phase | Carol Davis | 2024-05-16 | 2024-06-15 | In Progress
PJ004 | Development Sprint 1 | Dave Wilson | 2024-06-16 | 2024-07-31 | Delayed
PJ005 | Testing & QA | Eva Brown | 2024-08-01 | 2024-09-15 | Completed
PJ006 | Deployment & Training | Frank Miller | 2024-09-16 | 2024-10-31 | In Progress
Project Metrics | Values
Total Tasks | 6
Completed Tasks | 2 (33%)
In Progress Tasks | 3 (50%)
Delayed Tasks | 1 (17%)
Average Progress | 59%
Project Plan Dashboard View ¦ Generated on¦ Client Reporting Template