## Worksheet
Client Reporting - Project Plan - Data Version
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete | Description
T001 | Project Initiation | John Doe | 2024-04-01 | 2024-04-15 | Pending | 0% | Define project scope and objectives.
T002 | Requirements Gathering | Jane Smith | 2024-04-16 | 2024-05-15 | In Progress | 65% | Capture all client requirements and document.
T003 | Design Phase | Mike Johnson | 2024-05-16 | 2024-06-30 | Not Started | 0% | Create system architecture and UI mockups.
T004 | Development Phase | Sarah Brown | 2024-07-01 | 2024-11-30 | Not Started | 0% | Implement all features based on design.
T005 | Testing & QA | Lisa White | 2024-12-01 | 2025-01-31 | Not Started | 0% | Conduct comprehensive testing and bug fixes.
T006 | Client Review & Feedback | Alex Green | 2025-02-01 | 2025-03-15 | Not Started | 0% | Gather client feedback and finalize deliverables.
T007 | Deployment & Handover | Rachel Lee | 2025-03-16 | 2025-04-30 | Not Started | 0% | Publish final version and train client staff.
Total Project Duration: | [5 empty] | 2024-04-01 to 2025-04-30
Status Summary: | [5 empty] | Not Started: 5 tasks ¦ In Progress: 1 task ¦ Complete: 0 tasks