## Project Plan - Client Reporting
PROJECT PLAN - CLIENT REPORTING
Project Overview
Project Name | Client Reporting Dashboard Integration |  |  |  | Client | Global Solutions Inc.
Key Dates & Milestones
Phase | Milestone | Start Date | Due Date | Status
Discovery & Planning | Requirement Finalization | 2023-10-01 | 2023-10-15 | Completed
| Project Plan Approval | 2023-10-16 | 2023-10-25 | In Progress
Phase | Deliverable | Start Date | Due Date | Status
Design & Prototyping | UI/UX Wireframes - Phase 1 | 2023-10-26 | 2023-11-05 | Scheduled
| UI/UX Wireframes - Phase 2 | 2023-11-06 | 2023-11-15 | Scheduled
| Design Review (Client) | 2023-11-16 | 2023-11-25 | Scheduled
| Final Design Approval | 2023-11-26 | 2023-11-30 | Scheduled
Phase | Deliverable | Start Date | Due Date | Status
Development & Integration | Front-End Implementation - Phase 1 | 2023-12-01 | 2023-12-15 | Scheduled
| Front-End Implementation - Phase 2 | 2023-12-16 | 2023-12-30 | Scheduled
| Backend API Development - Phase 1 | 2024-01-01 | 2024-01-15 | Scheduled
| Backend API Development - Phase 2 | 2024-01-16 | 2024-01-31 | Scheduled
| Integration Testing (UI + Backend) | 2024-02-01 | 2024-02-15 | Scheduled
| Data Mapping & Validation (Legacy Systems) | 2024-02-16 | 2024-03-01 | Scheduled
Testing & Quality Assurance
Testing & QA | System Integration Test (SIT) | 2024-03-04 | 2024-03-15 | Scheduled
| UAT (User Acceptance Testing) | 2024-03-18 | 2024-04-15 | Scheduled
Deployment & Go-Live
Deployment | Staging Environment Setup | 2024-04-16 | 2024-04-30 | Scheduled
| Production Deployment & Go-Live | 2024-05-01 | 2024-05-15 | Scheduled
Project Timeline & Progress Summary
Total Duration | 21 weeks (04/16/2023 – 05/15/2024) | Overall Progress | 85% Complete
Team Responsibilities
Role | Name | Responsibilities
Project Manager | Jane Smith | Overall project delivery, client coordination, timeline management.
Lead Developer | Robert Chen | Front-end & back-end implementation, code quality assurance.
UI/UX Designer | Lisa Tran | Design system, wireframes, user experience flow.
QA Engineer | Daniel Park | Test planning, execution, bug tracking & reporting.