## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Assigned To | % Complete | Dependencies
1 | Project Initiation | 2023-10-01 | 2023-10-05 | Completed | Project Manager | 100% | N/A
2 | Requirements Gathering | 2023-10-06 | 2023-10-15 | In Progress | Business Analyst | 75% | 1
3 | Design Phase | 2023-10-16 | 2023-11-05 | Not Started | Lead Designer | 0% | 2
4 | Development Phase | 2023-11-06 | 2024-01-15 | Not Started | Development Team | 0% | 3
5 | Testing & QA | 2024-01-16 | 2024-02-15 | Not Started | QA Team | 0% | 4
6 | User Training & Documentation | 2024-02-16 | 2024-03-15 | Not Started | Training Specialist | 0% | 5
7 | Go-Live & Deployment | 2024-03-16 | 2024-03-31 | Not Started | DevOps Engineer | 0% | 6
8 | Post-Implementation Review | 2024-04-01 | 2024-04-15 | Not Started | Project Manager | 0% | 7