## Project Plan - Financial View
PROJECT PLAN - FINANCIAL VIEW
Phase/Task | Start Date | End Date | Budget (USD) | Actual (USD) | Variance (USD) | % Complete | Milestone Payments
[6 empty] | Planned | Received | Forecast | Pending | Status
Project Initiation & Planning | 2024-01-05 | 2024-01-19 | $5,000.00 | $4,856.33 | $143.67 | 97% | $2,500.00 | $2,500.00 | $2,500.01 | $-143.68 | Completed
Design & Architecture Development | 2024-01-22 | 2024-03-15 | $18,500.00 | $9,783.67 | $8,716.33 | 52% | $9,250.00 | $4,625.00 | $9,249.88 | $4,625.12 | In Progress
Development & Implementation | 2024-03-18 | 2024-06-30 | $75,350.00 | $38,791.54 | $36,558.46 | 51% | $22,605.00 | $11,302.50 | $22,604.99 | $11,302.49 | In Progress
Testing & Quality Assurance | 2024-07-03 | 2024-08-16 | $15,450.00 | $6,891.33 | $8,558.67 | 44% | $7,725.00 | $2,575.00 | $6,891.33 | $1,183.67 | In Progress
Deployment & Training | 2024-08-19 | 2024-09-30 | $17,850.00 | $3,678.45 | $14,171.55 | 21% | $8,925.00 | $-3,678.45 | $6,296.32 | $4,048.93 | Delayed (Pending)
Project Closure & Review | 2024-10-03 | 2024-10-17 | $6,550.00 | $87.99 | $6,462.01 | 1% | $3,275.00 | $-3275.01 | -$3,274.99 | $-3,274.98 | Pending Start
Total Project Costs |  |  | $148,700.00 | $64,189.31 | $84,510.69 | 52% | $54,285.00 | $27,733.94 | $64,189.31 | $36,451.06 | Overall: In Progress / At Risk
Note:All figures are in USD. Variance is calculated as Budget - Actual. Forecast and Pending values reflect expected future cash flow.