## Project Plan - Client Reporting
Project Plan - Client Reporting
Template Type:Project Plan ¦Style/Version:Home Use ¦Purpose:Client Reporting
Task ID | Task Description | Start Date | End Date | Status | Assigned To | % Complete
TASK001 | Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | Completed | Jane Doe | 100%
TASK002 | Requirements Gathering | 2024-01-16 | 2024-01-31 | In Progress | John Smith | 65%
TASK003 | Design Phase - Wireframes & Mockups | 2024-02-01 | 2024-02-15 | Not Started | Alice Brown | 0%
TASK004 | Development - Frontend Implementation | 2024-02-16 | 2024-03-15 | Not Started | Mike Johnson | 0%
TASK005 | Development - Backend Integration | 2024-03-16 | 2024-04-15 | Not Started | Sarah Wilson | 0%
TASK006 | User Acceptance Testing (UAT) | 2024-04-16 | 2024-05-15 | Not Started | Tony Reed | 0%
TASK007 | Final Review & Client Approval | 2024-05-16 | 2024-05-31 | Not Started | Jane Doe | 0%
Total Duration: | [5 empty] | 2024-01-15 to 2024-05-31