## Project Plan - Client Reporting
Project Plan - Client Reporting
Company Information
Name:GlobalTech Solutions Inc.
Contact:info@globaltechsolutions.com
Phone:+1 (555) 123-4567
Project Details
Project Name:Q4 Client Analytics Dashboard
Client:Apex Financial Group
Status:In Progress
Task ID | Description | Owner | Start Date | End Date | Status | Budget (USD)
P001 | Requirements Gathering & Client Workshops | Jane Doe, Project Manager | 2023-10-05 | 2023-10-15 | Completed | $8,500
P002 | UI/UX Design & Wireframing | Mark Lee, Lead Designer | 2023-10-16 | 2023-11-05 | In Progress | $12,000
P003 | Backend Development - Data Integration | Samira Patel, Senior Developer | 2023-11-06 | 2023-12-15 | In Progress | $35,000
P004 | Frontend Implementation & Dashboard Build | Carlos Mendez, Frontend Developer | 2023-12-16 | 2024-01-15 | In Progress | $30,000
P005 | Testing & QA – Performance & Security Validation | Lisa Chen, QA Lead | 2024-01-16 | 2024-01-31 | Delayed (Pending Approval) | $9,500
P006 | Client Training & Deployment | Jane Doe, Project Manager | 2024-02-01 | 2024-02-15 | Scheduled | $6,500
Generated on:April 5, 2025