## Project Plan - Client Reporting
PROJECT PLAN - CLIENT REPORTING
Task ID | Task Description | Start Date | End Date | Assigned To | Status | % Complete
P-001 | Project Initiation & Planning | 2025-04-01 | 2025-04-15 | Jane Smith | Pending | 0%
P-002 | Requirements Gathering | 2025-04-16 | 2025-04-30 | John Doe | In Progress | 65%
P-003 | Design Phase Completion | 2025-05-01 | 2025-05-14 | Alice Brown | In Progress | 40%
P-004 | Development & Implementation | 2025-05-15 | 2025-06-30 | Mike Johnson | Pending | 1%
P-005 | User Acceptance Testing (UAT) | 2025-07-01 | 2025-07-14 | Sarah Wilson | Pending | 0%
P-006 | Final Deployment & Handover | 2025-07-15 | 2025-07-31 | Daniel Lee | Pending | 0%
Project Completion Estimate: | [5 empty] | 22%