## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete
T001 | Project Initiation | John Doe | 2024-01-15 | 2024-01-25 | In Progress | 75%
T002 | Requirements Gathering | Jane Smith | 2024-01-26 | 2024-02-10 | Not Started | 0%
T003 | Design Phase | Mike Brown | 2024-02-11 | 2024-03-15 | Not Started | 0%
T004 | Development Phase | Sarah Wilson | 2024-03-16 | 2024-05-31 | Not Started | 0%
T005 | Testing & QA | Lisa Taylor | 2024-06-01 | 2024-07-15 | Not Started | 0%
T006 | Deployment | David Lee | 2024-07-16 | 2024-07-31 | Not Started | 0%
T007 | Closing & Reporting | John Doe | 2024-08-01 | 2024-08-15 | Not Started | 0%