## Project Plan - Client Reporting
Project Plan - Client Reporting
Prepared for: [Client Name] ¦ Report Date: [Date]
# | Task | Start Date | End Date | Duration (Days) | Assigned To | Status
1 | Project Initiation & Kickoff | 2024-01-05 | 2024-01-10 | 6 | Jane Smith | In Progress
2 | Requirement Gathering | 2024-01-11 | 2024-01-25 | 15 | Mike Johnson | In Progress
3 | Design Phase (UI/UX) | 2024-01-26 | 2024-02-15 | 21 | Sarah Lee | Not Started
4 | Development (Frontend) | 2024-02-16 | 2024-03-31 | 45 | Daniel Brown | Not Started
5 | Development (Backend) | 2024-02-16 | 2024-03-31 | 45 | Lisa Garcia | Not Started
6 | Integration & Testing | 2024-04-01 | 2024-04-30 | 30 | Alex Turner, Sarah Lee | Not Started
7 | User Acceptance Testing (UAT) | 2024-05-01 | 2024-05-15 | 15 | Jane Smith, Mike Johnson | Not Started
8 | Final Review & Deployment Prep | 2024-05-16 | 2024-05-31 | 16 | Lisa Garcia, Daniel Brown | Not Started
9 | Go-Live & Training Session | 2024-06-01 | 2024-06-15 | 15 | All Team Members | Not Started
This project plan is generated for client reporting purposes. For internal tracking, please refer to the master project management tool.