## Worksheet
Quarterly Project Plan - Client Reporting
Q3 2024 ¦ Project ID: PROJ-Q3-2024-001
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
P001 | Project Kickoff Meeting | Jane Smith | 2024-07-01 | 2024-07-03 | Completed | 100%
P002 | Requirements Gathering | Mike Johnson | 2024-07-04 | 2024-07-15 | In Progress | 65%
P003 | Design Phase - UI/UX | Sarah Lee | 2024-07-16 | 2024-08-15 | Not Started | 0%
P004 | Development - Backend API | David Kim | 2024-08-16 | 2024-09-30 | Not Started | 0%
P005 | Development - Frontend Interface | Lisa Brown | 2024-08-16 | 2024-09-30 | Not Started | 0%
P006 | Testing & QA Phase | Raj Patel | 2024-10-01 | 2024-10-15 | Not Started | 0%
P007 | User Acceptance Testing (UAT) | Emma Wilson | 2024-10-16 | 2024-10-31 | Not Started | 0%
P008 | Deployment & Go-Live | Tony Garcia | 2024-11-01 | 2024-11-05 | Not Started | 0%
Total Project Progress: | [5 empty] | 27%