## Project Plan - Startup
Project Plan - Startup Client Reporting
Task ID | Task Description | Owner | Start Date | End Date | Status
P001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | Completed
P002 | Requirements Gathering & Documentation | John Smith | 2024-03-16 | 2024-03-31 | In Progress
P003 | UI/UX Design Phase 1 | Emily Chen | 2024-04-01 | 2024-04-15 | Pending
P004 | Frontend Development (Module A) | Michael Brown | 2024-04-16 | 2024-05-15 | Pending
P005 | Backend API Integration Testing | Sarah Wilson | 2024-05-16 | 2024-06-15 | Pending
P006 | User Acceptance Testing (UAT) | David Lee | 2024-06-16 | 2024-07-15 | Pending
P007 | Final Review & Client Sign-off | Jane Doe | 2024-07-16 | 2024-07-31 | Pending
P008 | Project Deployment & Go-Live | Michael Brown | 2024-08-01 | 2024-08-15 | Pending
P009 | Post-Launch Review & Reporting | Sarah Wilson | 2024-08-16 | 2024-08-31 | Pending
P010 | Client Feedback Collection & Retrospective | Emily Chen | 2024-09-01 | 2024-09-15 | Pending
Total Tasks: |  |  |  |  | 10
Prepared for Client Reporting – Project Plan ¦ Startup Version ¦ Updated: March 15, 2024