## Project Plan - Tracking View
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete
TASK-001 | Project Kickoff Meeting | John Doe | 2024-04-15 | 2024-04-15 | Completed | 100%
TASK-002 | Requirements Gathering | Jane Smith | 2024-04-16 | 2024-04-30 | In Progress
TASK-003 | Design Phase - UI/UX | Mike Johnson | 2024-05-01 | 2024-05-15 | In Progress
TASK-004 | Development - Frontend | Sarah Lee | 2024-05-16 | 2024-06-15 | Not Started
TASK-005 | Development - Backend | David Kim | 2024-05-16 | 2024-06-30 | Not Started
TASK-006 | Testing & QA | Alice Brown | 2024-07-01 | 2024-07-15 | Not Started
TASK-007 | User Training & Documentation | Robert White | 2024-07-16 | 2024-07-31 | Not Started
TASK-008 | Project Closure & Reporting | John Doe | 2024-08-01 | 2024-08-15 | Not Started
Overall Progress: | [5 empty] | 35%
Notes:This tracking view is updated weekly. Status indicators follow standard project management conventions.