## Worksheet
Weekly Project Plan - Client Reporting
Week of: [Insert Start Date] to [Insert End Date]
Task ID | Task Description | Owner | Start Date | Due Date | Status | Progress (Week)
T001 | Client Requirements Gathering | Jane Smith | 2024-05-27 | 2024-05-31 | Pending | 0% / 10%
T002 | Design Mockups and Wireframes | Mike Johnson | 2024-05-31 | 2024-06-07 | In Progress | 55% / 75%
T003 | Development Phase I - UI Implementation | Carlos Mendez | 2024-06-03 | 2024-06-11 | In Progress | 85% / 95%
T004 | Backend Integration Testing | Anna Patel | 2024-06-15 | 2024-06-17 | Pending | 0% / 15%
T005 | Client Feedback Review & Iteration | Sarah Lee | 2024-06-18 | 2024-06-19 | Pending | 0% / 5%
T006 | Initial Project Kickoff Meeting | James Carter | 2024-05-27 | 2024-05-31 | Completed | 100% / 100%
Total Tasks: | [5 empty] | 6 | Completed: 1 | In Progress: 2
Note: This report is updated weekly. Please verify actual progress with project manager.