## Worksheet
Client Reporting - Project Template (Detailed)
Project ID | Project Name | Client Name | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD)
PJ-2024-001 | Enterprise CRM Integration | GlobalTech Inc. | Jan 15, 2024 | Jun 30, 2024 | In Progress | $150,000.00 | $89,756.34
PJ-2024-002 | Digital Marketing Campaign 2.0 | Sparkle Brands LLC | Mar 10, 2024 | Sep 15, 2024 | On Hold (Client Approval Pending) | $75,000.00 | $38,911.56
PJ-2024-003 | Website Redesign & SEO Optimization | UrbanStyle Fashion Co. | Feb 5, 2024 | May 31, 2024 | Closed - Delivered | $65,000.00 | $64,873.19
PJ-2024-004 | Mobile App Development (iOS & Android) | NexaHealth Solutions | Jan 8, 2024 | Dec 15, 2024 | In Progress | $300,000.00 | $175,431.87
PJ-2024-005 | Cloud Infrastructure Migration | FinServe Global | Apr 1, 2024 | Oct 31, 2024 | In Progress - Phase 1 Complete | $185,000.00 | $96,345.72
PJ-2024-006 | AI-Powered Customer Support Chatbot | ServiConnect Inc. | Mar 18, 2024 | Aug 31, 2024 | In Progress - Testing Phase | $105,000.00 | $67,389.55
PJ-2024-007 | Enterprise Data Analytics Dashboard | QuantumMetrics LLC | Feb 14, 2024 | Jul 31, 2024 | Closed - Delivered (Final Review) | $95,000.00 | $93,678.41
PJ-2024-008 | ERP System Upgrade & Training | LogiCore Industries | Jan 23, 2024 | Nov 15, 2024 | In Progress - Implementation Phase | $145,000.00 | $78,916.33
PJ-2024-009 | Supply Chain Visibility Platform (Pilot) | TransGlobal Logistics | May 1, 2024 | Sep 30, 2024 | In Progress - Development Phase | $88,500.00 | $39,617.89
PJ-2024-010 | Employee Onboarding Portal Redesign | Horizon HR Solutions | Feb 28, 2024 | Aug 31, 2024 | In Progress - UI/UX Review | $55,000.00 | $33,978.15
Total Projects: | [5 empty] | $1,228,500.00 | $797,453.38
Budget Utilization: | [5 empty] | 64.9%
Report generated on May 3, 2024 ¦ Project Template Version: Detailed v3.1