## Worksheet
Client Reporting - Project Template
Prepared for: [Client Name]
Project: [Project Title]
Date: [Reporting Date]
Task ID | Task Description | Status | Start Date | End Date | Budget (USD) | Actual Cost (USD)
T001 | Project Planning & Kick-off | Completed | 2023-10-01 | 2023-10-15 | $5,000.00 | $4,856.75
T002 | Requirements Gathering | In Progress | 2023-10-16 | 2023-11-05 | $8,500.00 | $7,945.33
T003 | Design Phase (UI/UX) | Not Started | 2023-11-06 | 2023-11-30 | $6,750.00 | $0.00
T004 | Development - Backend | Not Started | 2023-12-01 | 2024-01-15 | $18,900.00 | $0.00
T005 | Development - Frontend | Not Started | 2023-12-15 | 2024-01-31 | $16,500.00 | $0.00
T006 | Testing & QA | Not Started | 2024-02-01 | 2024-03-15 | $9,800.00 | $0.00
T007 | Deployment & Go-Live | Not Started | 2024-03-16 | 2024-03-31 | $5,500.00 | $0.00
Total Project Summary: |  |  |  |  | $71,450.00 | $12,802.08
Document generated on: [Current Date]
This report is intended for internal client review and may contain confidential information.