## Worksheet
Quarterly Client Report
Project Template - Q3 2024
Task/Activity | Description | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
Project Initiation & Planning | Finalize project scope, deliverables, and timelines with client approval. | Jul 1, 2024 | Jul 10, 2024 | Jul 1, 2024 | Jul 9, 2024 | Complete
Requirements Gathering Session | Conduct workshops with stakeholders to document functional requirements. | Jul 11, 2024 | Jul 18, 2024 | Jul 15, 2024 | Jul 17, 2024 | Complete
Design Phase (UI/UX) | Create wireframes and high-fidelity mockups for client approval. | Jul 19, 2024 | Aug 5, 2024 | Jul 19, 2024 | Aug 6, 2024 | Complete
Development Sprint #1 | Implement core module: User Authentication & Dashboard. | Aug 6, 2024 | Aug 19, 2024 | Aug 6, 2024 | Aug 18, 2024 | Complete
Development Sprint #2 | Develop Reporting Engine and Data Export Features. | Aug 20, 2024 | Sep 1, 2024 | Aug 19, 2024 | Sep 1, 2024 | Complete
Testing & QA Phase | Execute test cases, bug fixes, and performance optimization. | Sep 2, 2024 | Sep 15, 2024 | Sep 3, 2024 | Sep 16, 2024 | Complete
User Training & Documentation | Prepare training materials and conduct onboarding sessions. | Sep 16, 2024 | Sep 23, 2024 | Sep 17, 2024 | Sep 19, 2024 | Complete
Project Closure & Handover | Final review with client, handover of deliverables and support plan. | Sep 24, 2024 | Sep 30, 2024 | Sep 30, 2024 | Sep 30, 2024 | Complete