## Worksheet
Project Timeline Report
Client Reporting - Advanced Template Version 2.0
Phase/Task | Start Date | End Date | Status | Owner | % Complete
Project Initiation & Planning
Project Kick-off Meeting | 2023-10-01 | 2023-10-05 | Completed | Jane Doe | 100%
Requirements Gathering | 2023-10-06 | 2023-10-15 | Completed | John Smith | 100%
Project Scope Finalization | 2023-10-16 | 2023-10-20 | Completed | Jane Doe | 100%
Design & Development Phase
UI/UX Design Prototypes | 2023-10-21 | 2023-11-05 | In Progress | Alice Johnson | 65%
Frontend Development | 2023-11-06 | 2023-12-15 | In Progress | Robert Brown | 45%
Backend Development | 2023-11-06 | 2024-01-31 | In Progress | Lisa Wong | 55%
Testing & Quality Assurance
Unit Testing & Integration | 2024-02-01 | 2024-03-15 | Delayed | Maria Garcia | 30%
User Acceptance Testing (UAT) | 2024-03-16 | 2024-04-15 | Delayed | Daniel Lee | 15%
Deployment & Go-Live
Production Deployment | 2024-04-16 | 2024-05-15 | Delayed | Sophia Patel | 5%
Post-Launch Support & Review | 2024-05-16 | 2024-06-30 | Delayed | James Wilson | 0%
Total Project Duration | 2023-10-01 to 2024-06-30 |  | Overall Delayed | Average Progress: 48%